## Parts
Part Section | Part Name | Image | Note | Link | Cost | Cost Range | Cost Est for Proj Proposal
Microcontroller | Microcontroller Arduino Nano | #VALUE! |  | https://www.diyelectronics.co.za/store/boards/10-nano-board-based-on-arduino.html?ut | 126 | R80-R200 | 160
Motor Drivers | L298N Dual H-Bridge | #VALUE! |  | https://www.communica.co.za/products/bdd-dual-motor-driver-l298-screw?variant=47620048978220&sfdr_ptcid=31591_617_701055987&sfdr_hash=4042dc5fa79365b5e35299634508ce03&utm_source=www.communica.co.za&gad_source=1&gad_campaignid=22552818411&gclid=CjwKCAjwpcTNBhA5EiwAdO1S9j8BpageufICOW-Z6TCuTOHkJjV4mgwHRsQ9F622epTADRpw2i9B4RoCQCsQAvD_BwE | 39
| BTS7960 motor driver | #VALUE! |  | https://www.communica.co.za/products/hkd-forw-revse-motor-control-12v?variant=49873343971628&sfdr_ptcid=31591_617_711238132&sfdr_hash=039a782ee6f0c5df5f561b78fac1f12e&utm_source=www.communica.co.za&gad_source=1&gad_campaignid=22552818411&gclid=CjwKCAjwpcTNBhA5EiwAdO1S9jU8M_wyGrW8C2IMtM_qbdIicQxaAn56mAuL4-oNno3XAdqg1n5jthoCBfIQAvD_BwE | 160
| Sabertooth dual motor controller | #VALUE! |  | https://www.communica.co.za/products/hkd-dual-dc-motor-shield-l298?variant=44293656052012&sfdr_ptcid=31591_617_694882795&sfdr_hash=2ffc78cdaad3a413574e2cc754c9573b&utm_source=www.communica.co.za&gad_source=1&gad_campaignid=20668254388&gclid=CjwKCAjwpcTNBhA5EiwAdO1S9sH-wSt8uWUmpioJwDIlQHJc6sZka1xTwFbTV_Lzu6WjE5FxsALwzRoCC1AQAvD_BwE | 205
| DRV8833 driver | #VALUE! |  | https://www.fruugo.co.za/double-dcmotor-control-board-direction-adjustment-27-108v-voltages-ranges-for-diy-electronics-projects-multicolor/p-440292550-923805585?language=en&ac=google&utm_source=google&utm_medium=paid&asc=pmax&gad_source=1&gad_campaignid=22994512251&gclid=CjwKCAjwpcTNBhA5EiwAdO1S9lOQaII__z-Y2b5_sexgFMlUdn1pfXsscPT0ZvQwo3Rx_wYw_qkiuBoCn7wQAvD_BwE | 189
Drive Motors | N20 metal gear motors | #VALUE! |  | https://www.communica.co.za/?gad_source=1&gad_campaignid=22552818411&gclid=CjwKCAjwpcTNBhA5EiwAdO1S9jmN8wJXmn6ti2nsNR3tHCBeIpAHcd2ph_qDgQuX5Nadhe9cyrFitxoCVeMQAvD_BwE | 70 | R50 - R600 | 200
| Pololu micro metal gearmotors |  | Communica sells them as well, couldn't find exact lsiting | https://www.communica.co.za/?gad_source=1&gad_campaignid=22552818411&gclid=CjwKCAjwpcTNBhA5EiwAdO1S9jmN8wJXmn6ti2nsNR3tHCBeIpAHcd2ph_qDgQuX5Nadhe9cyrFitxoCVeMQAvD_BwE
37 mm DC gear motors
| High-torque planetary motors | #VALUE! |  | https://www.communica.co.za/products/bdd-worm-gear-motor-12v-23rpm?variant=49957877580076&sfdr_ptcid=31591_617_710181157&sfdr_hash=ecbe90511a170b5f53e6d24d5b7cf269&ut | 160
Wheels / Traction System | High-grip rubber wheels |  | Communica, look for cheaper alternatives |  | 300 | R80-R300(*) | 400
| Silicone traction wheels | #VALUE! | only for x2 | https://www.communica.co.za/products/bmt-wheels-x2-all-terrain-chrome?variant=47729631920428&sfdr_ptcid=31591_617_701308473&sfdr_hash=311d54ce70ae9cfdf5897b1d9114acd8&utm_source=www.communica.co.za&gad_source=1&gad_campaignid=20668254388&gclid=CjwKCAjwpcTNBhA5EiwAdO1S9kXhBHfpWaQHgYQKM_77kregkGhHilZJcfRTNXhUQ_R7iHqjRsSXUhoCWHIQAvD_BwE | 239
Tank tracks
Custom CNC wheels
Opponent Detection Sensors | Ultrasonic sensors |  |  |  | Spare parts | R30-R100 | 20
| Infrared distance sensors | #VALUE! |  | https://www.communica.co.za/products/bmt-ir-obstacle-avoidance-sensor?variant=31803174682697&sfdr_ptcid=31591_617_658494889&sfdr_hash=a8b99bb606920d53e8314ca65226a078&utm_source=www.communica.co.za&gad_source=1&gad_campaignid=22552818411&gclid=CjwKCAjwpcTNBhA5EiwAdO1S9kDcV41SIaxM5JfPZq425go9QTQawLk1FMPdXLE_xVcJQG0oLwdRjBoCdRoQAvD_BwE | 14
| Time-of-flight sensors |  |  |  | 170
LIDAR (advanced)
Edge Detection Sensors | Reflectance sensors |  |  |  |  | R50-R300
IR line sensors
QTR reflectance sensor arrays
Motion sensors | Accelerometer + gyro modules |  |  |  |  | Optional (*) | 0
Power System | LiPo battery (7.4 V or 11.1 V) |  |  | RS components | 573 | R150-R800 | 600
18650 Li-ion battery pack
Voltage regulators
Power switch
Mechanical Structure | 3D printed general frame |  |  |  |  | R200 - R1000 | 1000
Sheet metal shoving part
Additional Electronics | Capacitors |  |  |  |  | R50-R200 | 200
PCB
Switches
| Jumper wires |  | Used mostly for testing, not official design |  | N/A
Mechanical Hardware | Screws and bolts |  |  |  |  | R50 - R300 | 300
Bearings
Gearboxes
Weight plates
Magnets (for traction) (*)
[6 empty] | TOTAL | 2880

## Cost
Activity | Engineering Time |  | Running Costs | Facility Use | Capital Costs | MMW |  | MMW | TOTAL
[6 empty] | Labour |  | Material
| hr | R | R | R | R | hr | R | R | R
Review Literature | 25 | 12500 | [6 empty] | 12500
Identify Compatible Design Approaches | 30 | 15000 | [6 empty] | 15000
Compile Design Requirements | 20 | 10000 | [6 empty] | 10000
Investigate Concepts for the Robot System | 50 | 25000 |  | 200 |  |  |  |  | 25200
Simulate the Most Promising Concepts | 60 | 30000 |  | 300 |  |  |  |  | 30300
Select Preferred Concept | 20 | 10000 | [6 empty] | 10000
Design Review | 5 | 2500 | [6 empty] | 2500
Design Prototype System | 50 | 25000 | 800 | [5 empty] | 25800
Manufacture Prototype | 60 | 30000 | 1800 | 300 |  | 2 | 700 | 200 | 33000
Test Prototype | 50 | 25000 | 200 | 300 | 150 |  |  |  | 25650
Improve Prototype and Validate System Performance | 80 | 40000 | 80 | 200 |  |  |  |  | 40280
Finalise Report | 100 | 50000 | [6 empty] | 50000
TOTAL | 550 | 275000 | 2880 | 1300 | 150 | 2 | 700 | 200 | 280230
Activity | Engineering Time |  | Running Costs | Facility Use | Capital Costs | MMW |  | MMW | TOTAL
[6 empty] | Labour |  | Material
| hr | R | R | R | R | hr | R | R | R
Review Literature | 25 | 0 | [6 empty] | 0
Identify Compatible Design Approaches | 30 | 0 | [6 empty] | 0
Compile Design Requirements | 20 | 0 | [6 empty] | 0
Investigate Concepts for the Robot System | 50 | 0 | [6 empty] | 0
Simulate the Most Promising Concepts | 60 | 0 |  | 80 |  |  |  |  | 80
Select Preferred Concept | 20 | 0 | [6 empty] | 0
Design Review | 5 | 0 | [6 empty] | 0
Design Prototype System | 50 | 0 | 700 | [5 empty] | 700
Manufacture Prototype | 60 | 0 | 1800 |  |  | 2 | 700 | 200 | 2700
Test Prototype | 50 | 0 | 200 |  | 150 |  |  |  | 350
Improve Prototype and Validate System Performance | 80 | 0 | 80 | [5 empty] | 80
Finalise Report | 100 | 0 | [6 empty] | 0
TOTAL | 550 | 0 | 2780 | 80 | 150 | 2 | 700 | 200 | 3910

## Gannt
Activity | Feb 20206 | Mar 2026 | Apr 2026 | May 2026 | Jun 2026 | Jul 2026 | Aug 2026 | Sep 20206 | Oct 2026
Review Literature
Identify Compatible Design Approaches
Compile Design Requirements
Investigate Concepts for the Robot System
Simulate the Most Promising Concepts
Select Preferred Concept
Design Review
Design Prototype System
Manufacture Prototype
Test Prototype
Improve Prototype and Validate System Performance
Finalise Report